## PCS Workplan v8
ACTC PCS SaaS Replacement — Development Workplan v8
Alameda County Transportation Commission ¦ Cole Management & Engineering
Date: April 19, 2026 ¦ Contract kickoff: May 1, 2026 ¦ Rates: B7 R26-003 2026 baseline, 3% Jan 1 escalation ¦ v8 adds Status column — all rows Not Started (contract has not yet begun)
WBS | Task / Deliverable | Start | Finish | Resource | Hours | Cost | Notes | Status
1 | PHASE 1: CORE MVP (May – Oct 2026) | 2026-05-01 | 2026-10-30
1.0 | Database Learning & Restructuring (Deliverable: Data Dictionary) | 2026-05-01 | 2026-06-19
1.0.1 | Legacy DB inventory — map 426 tables, 184 views, 61 AccuFund sync, identify active vs legacy | 2026-05-01 | 2026-05-29 | Nassayan | 40 |  | Full table/view walkthrough | Not Started
1.0.1 | Legacy DB inventory — map 426 tables, 184 views, 61 AccuFund sync, identify active vs legacy | 2026-05-01 | 2026-05-29 | Cole | 20 |  | Paired with Tom | Not Started
1.0.2 | Data dictionary — table purpose, column definitions, relationships, report lineage | 2026-05-18 | 2026-06-12 | Nassayan | 32 |  | Living doc | Not Started
1.0.2 | Data dictionary — table purpose, column definitions, relationships, report lineage | 2026-05-18 | 2026-06-12 | Cole | 24 |  |  | Not Started
1.0.3 | Findings package — feeds schema design (1.1.1) and cleanup plan (1.11) | 2026-06-01 | 2026-06-19 | Nassayan | 24 |  | Input to 1.1.1 and 1.11 | Not Started
1.0.3 | Findings package — feeds schema design (1.1.1) and cleanup plan (1.11) | 2026-06-01 | 2026-06-19 | Cole | 20 |  | Input to 1.1.1 and 1.11 | Not Started
1.1 | Infrastructure & Architecture | 2026-05-01 | 2026-06-27
1.1.1 | Supabase schema design, RLS policies, audit trail | 2026-05-01 | 2026-05-23 | Cole | 52 |  |  | Not Started
1.1.1 | Supabase schema design, RLS policies, audit trail | 2026-05-01 | 2026-05-23 | Brown | 40 |  |  | Not Started
1.1.1 | Supabase schema design, RLS policies, audit trail | 2026-05-01 | 2026-05-23 | Nassayan | 60 |  | DB schema lead | Not Started
1.1.2 | Auth system (Google + Microsoft OAuth) | 2026-05-05 | 2026-05-16 | Cole | 16 |  |  | Not Started
1.1.2 | Auth system (Google + Microsoft OAuth) | 2026-05-05 | 2026-05-16 | Brown | 16 |  |  | Not Started
1.1.3 | Workflow engine & visual editor | 2026-05-12 | 2026-06-06 | Cole | 52 |  |  | Not Started
1.1.3 | Workflow engine & visual editor | 2026-05-12 | 2026-06-06 | Brown | 48 |  |  | Not Started
1.1.3 | Workflow engine & visual editor | 2026-05-12 | 2026-06-06 | Mortazavi | 16 |  | AI workflow patterns | Not Started
1.1.4 | Notification system, email templates, delegation | 2026-05-19 | 2026-06-13 | Cole | 28 |  |  | Not Started
1.1.4 | Notification system, email templates, delegation | 2026-05-19 | 2026-06-13 | Brown | 28 |  |  | Not Started
1.1.5 | Home dashboard & "In Your Court" work queue | 2026-06-01 | 2026-06-19 | Cole | 28 |  |  | Not Started
1.1.5 | Home dashboard & "In Your Court" work queue | 2026-06-01 | 2026-06-19 | Brown | 32 |  |  | Not Started
1.1.6 | BigQuery sync pipeline setup | 2026-06-08 | 2026-06-27 | Nassayan | 48 |  | BQ analytics layer | Not Started
1.1.6 | BigQuery sync pipeline setup | 2026-06-08 | 2026-06-27 | Cole | 12 |  |  | Not Started
1.1.7 | Infrastructure testing & compliance review | 2026-06-16 | 2026-06-27 | Salzwedel | 12 |  | ACTC compliance | Not Started
1.1.7 | Infrastructure testing & compliance review | 2026-06-16 | 2026-06-27 | Chang | 16 |  |  | Not Started
1.1.7 | Infrastructure testing & compliance review | 2026-06-16 | 2026-06-27 | Lee | 16 |  |  | Not Started
M1 | ★ Infrastructure Complete (Auth, RLS, Workflow Engine) |  | 2026-06-27
1.2 | Programming Module | 2026-06-02 | 2026-07-10
1.2.1 | Programming data model & fund source management | 2026-06-02 | 2026-06-20 | Cole | 36 |  |  | Not Started
1.2.1 | Programming data model & fund source management | 2026-06-02 | 2026-06-20 | Nassayan | 32 |  | DB tables/views | Not Started
1.2.1 | Programming data model & fund source management | 2026-06-02 | 2026-06-20 | Brown | 28 |  |  | Not Started
1.2.2 | CIP amendment workflow & allocation tracking | 2026-06-15 | 2026-07-03 | Cole | 24 |  |  | Not Started
1.2.2 | CIP amendment workflow & allocation tracking | 2026-06-15 | 2026-07-03 | Brown | 24 |  |  | Not Started
1.2.3 | Programming UI, search, filter, print/export | 2026-06-22 | 2026-07-10 | Cole | 16 |  |  | Not Started
1.2.3 | Programming UI, search, filter, print/export | 2026-06-22 | 2026-07-10 | Brown | 20 |  |  | Not Started
1.2.4 | Programming module documentation | 2026-07-01 | 2026-07-10 | Nipper | 20 |  | User guide + admin docs | Not Started
1.3 | Projects Module | 2026-07-01 | 2026-08-07
1.3.1 | Project data model, PNRF workflow, cost codes | 2026-07-01 | 2026-07-18 | Cole | 36 |  |  | Not Started
1.3.1 | Project data model, PNRF workflow, cost codes | 2026-07-01 | 2026-07-18 | Nassayan | 32 |  | DB tables/views | Not Started
1.3.1 | Project data model, PNRF workflow, cost codes | 2026-07-01 | 2026-07-18 | Brown | 32 |  |  | Not Started
1.3.2 | Project forecasts, PM Update view, Cost/Schedule Reports | 2026-07-14 | 2026-08-07 | Cole | 44 |  |  | Not Started
1.2.5 | Programming module testing | 2026-07-06 | 2026-07-10 | Chang | 12 |  |  | Not Started
1.2.5 | Programming module testing | 2026-07-06 | 2026-07-10 | Lee | 12 |  |  | Not Started
1.3.2 | Project forecasts, PM Update view, Cost/Schedule Reports | 2026-07-14 | 2026-08-07 | Brown | 32 |  |  | Not Started
1.3.3 | Projects module documentation | 2026-07-28 | 2026-08-07 | Nipper | 20 |  |  | Not Started
1.4 | Contracts Module | 2026-07-14 | 2026-09-04
1.4.1 | Contract data model, tasks, vendors, commitments | 2026-07-14 | 2026-08-07 | Cole | 44 |  |  | Not Started
1.4.1 | Contract data model, tasks, vendors, commitments | 2026-07-14 | 2026-08-07 | Nassayan | 40 |  | DB tables/views | Not Started
1.3.4 | Projects module testing | 2026-08-03 | 2026-08-07 | Chang | 12 |  |  | Not Started
1.3.4 | Projects module testing | 2026-08-03 | 2026-08-07 | Lee | 12 |  |  | Not Started
1.4.1 | Contract data model, tasks, vendors, commitments | 2026-07-14 | 2026-08-07 | Brown | 40 |  |  | Not Started
1.4.2 | C1/C2 forms, amendments, changes, documents | 2026-08-03 | 2026-08-21 | Cole | 36 |  |  | Not Started
1.4.2 | C1/C2 forms, amendments, changes, documents | 2026-08-03 | 2026-08-21 | Brown | 32 |  |  | Not Started
1.4.3 | Contract workflows (WF-09/10), M contract, PO entry | 2026-08-11 | 2026-09-04 | Cole | 32 |  |  | Not Started
1.4.3 | Contract workflows (WF-09/10), M contract, PO entry | 2026-08-11 | 2026-09-04 | Brown | 32 |  |  | Not Started
1.4.4 | Time-phased budgets (WF-24), Budget Change Req (WF-23) | 2026-08-24 | 2026-09-04 | Cole | 20 |  |  | Not Started
1.4.4 | Time-phased budgets (WF-24), Budget Change Req (WF-23) | 2026-08-24 | 2026-09-04 | Brown | 24 |  |  | Not Started
1.4.5 | Contracts module documentation | 2026-08-25 | 2026-09-04 | Nipper | 20 |  |  | Not Started
1.4.6 | Contracts compliance review | 2026-08-25 | 2026-09-04 | Salzwedel | 12 |  |  | Not Started
1.4.7 | Contracts module testing | 2026-08-31 | 2026-09-04 | Chang | 12 |  |  | Not Started
1.4.7 | Contracts module testing | 2026-08-31 | 2026-09-04 | Lee | 12 |  |  | Not Started
M2 | ★ Core Modules Complete (Programming, Projects, Contracts) |  | 2026-09-18
1.5 | Invoice Module (with AI Intake & Compliance) | 2026-08-18 | 2026-10-16
1.5.1 | AI Invoice Intake — Document ingestion pipeline | 2026-08-18 | 2026-09-05 | Mortazavi | 56 |  | Claude API PDF/image extraction | Not Started
1.5.1 | AI Invoice Intake — Document ingestion pipeline | 2026-08-18 | 2026-09-05 | Cole | 20 |  |  | Not Started
1.5.1 | AI Invoice Intake — Document ingestion pipeline | 2026-08-18 | 2026-09-05 | Brown | 28 |  |  | Not Started
1.5.2 | AI Invoice Intake — Field extraction & pre-population | 2026-09-01 | 2026-09-19 | Mortazavi | 48 |  | Prompt eng, field mapping | Not Started
1.5.2 | AI Invoice Intake — Field extraction & pre-population | 2026-09-01 | 2026-09-19 | Brown | 32 |  | Prepopulated form UI | Not Started
1.5.2 | AI Invoice Intake — Field extraction & pre-population | 2026-09-01 | 2026-09-19 | Cole | 16 |  |  | Not Started
1.5.3 | AI Invoice Intake — Compliance analysis engine | 2026-09-08 | 2026-09-26 | Mortazavi | 48 |  | Rate/budget/cost code/date checks | Not Started
1.5.3 | AI Invoice Intake — Compliance analysis engine | 2026-09-08 | 2026-09-26 | Cole | 16 |  |  | Not Started
1.5.3 | AI Invoice Intake — Compliance analysis engine | 2026-09-08 | 2026-09-26 | Brown | 24 |  | Compliance panel UI | Not Started
1.5.3 | AI Invoice Intake — Compliance analysis engine | 2026-09-08 | 2026-09-26 | Nassayan | 20 |  | Contract rate/budget queries | Not Started
1.5.4 | AI Invoice Intake — Review dashboard & override UI | 2026-09-15 | 2026-10-03 | Brown | 28 |  | Accept/correct/override flow | Not Started
1.5.4 | AI Invoice Intake — Review dashboard & override UI | 2026-09-15 | 2026-10-03 | Cole | 12 |  |  | Not Started
1.5.4 | AI Invoice Intake — Review dashboard & override UI | 2026-09-15 | 2026-10-03 | Mortazavi | 20 |  |  | Not Started
1.5.5 | Invoice data model, PSA/PFA entry paths | 2026-09-08 | 2026-09-26 | Cole | 36 |  |  | Not Started
1.5.5 | Invoice data model, PSA/PFA entry paths | 2026-09-08 | 2026-09-26 | Nassayan | 48 |  | DB tables/views | Not Started
1.5.5 | Invoice data model, PSA/PFA entry paths | 2026-09-08 | 2026-09-26 | Brown | 32 |  |  | Not Started
1.5.6 | Approval routing (WF-03), Short Pay (WF-06), Retention (WF-07) | 2026-09-15 | 2026-10-03 | Cole | 32 |  |  | Not Started
1.5.6 | Approval routing (WF-03), Short Pay (WF-06), Retention (WF-07) | 2026-09-15 | 2026-10-03 | Brown | 28 |  |  | Not Started
1.5.7 | IPV/CSR generation, check run (WF-08), Invoice Status Log | 2026-09-22 | 2026-10-16 | Cole | 28 |  | Replaces Excel ISL | Not Started
1.5.7 | IPV/CSR generation, check run (WF-08), Invoice Status Log | 2026-09-22 | 2026-10-16 | Brown | 28 |  |  | Not Started
1.5.7 | IPV/CSR generation, check run (WF-08), Invoice Status Log | 2026-09-22 | 2026-10-16 | Nassayan | 20 |  | BQ reporting views | Not Started
1.5.8 | Invoice module documentation (incl AI Intake guide) | 2026-10-05 | 2026-10-16 | Nipper | 28 |  |  | Not Started
1.5.9 | Invoice compliance review | 2026-10-05 | 2026-10-16 | Salzwedel | 12 |  |  | Not Started
1.5.10 | Invoice module testing (incl AI Intake accuracy) | 2026-10-05 | 2026-10-16 | Chang | 32 |  |  | Not Started
1.5.10 | Invoice module testing (incl AI Intake accuracy) | 2026-10-05 | 2026-10-16 | Lee | 32 |  |  | Not Started
1.6 | Funding Module | 2026-09-21 | 2026-10-16
1.6.1 | Funding data model (grants, allotments, DIAs, PFA grants) | 2026-09-21 | 2026-10-09 | Cole | 28 |  |  | Not Started
1.6.1 | Funding data model (grants, allotments, DIAs, PFA grants) | 2026-09-21 | 2026-10-09 | Nassayan | 40 |  | DB tables/views | Not Started
1.6.1 | Funding data model (grants, allotments, DIAs, PFA grants) | 2026-09-21 | 2026-10-09 | Brown | 24 |  |  | Not Started
1.6.2 | Funding UI, closeout workflows, print/export | 2026-10-01 | 2026-10-16 | Cole | 12 |  |  | Not Started
1.6.2 | Funding UI, closeout workflows, print/export | 2026-10-01 | 2026-10-16 | Brown | 16 |  |  | Not Started
1.6.4 | Funding module testing | 2026-10-12 | 2026-10-16 | Chang | 12 |  |  | Not Started
1.6.4 | Funding module testing | 2026-10-12 | 2026-10-16 | Lee | 12 |  |  | Not Started
1.6.3 | Funding module documentation | 2026-10-08 | 2026-10-16 | Nipper | 12 |  |  | Not Started
M3 | ★ All Core Modules Complete (Invoice + Funding workflows) |  | 2026-10-30
1.11 | PCS Data Review & Cleanup (parallel to module builds, gates Migration) | 2026-06-15 | 2026-10-16
1.11.1 | Cleanup plan — scope, priorities, data quality rules, table owners | 2026-06-15 | 2026-07-03 | Cole | 16 |  | Uses 1.0.3 findings | Not Started
1.11.1 | Cleanup plan — scope, priorities, data quality rules, table owners | 2026-06-15 | 2026-07-03 | Nipper | 20 |  | Documentation lead | Not Started
1.11.2 | Programming & Projects data review — fund sources, allocations, project master | 2026-07-06 | 2026-08-14 | Nipper | 32 |  |  | Not Started
1.11.2 | Programming & Projects data review — fund sources, allocations, project master | 2026-07-06 | 2026-08-14 | Salzwedel | 16 |  |  | Not Started
1.11.2 | Programming & Projects data review — fund sources, allocations, project master | 2026-07-06 | 2026-08-14 | Chang | 36 |  |  | Not Started
1.11.2 | Programming & Projects data review — fund sources, allocations, project master | 2026-07-06 | 2026-08-14 | Lee | 36 |  |  | Not Started
1.11.3 | Contracts & Invoice data review — C1/C2, vendors, invoices, check runs | 2026-08-10 | 2026-09-18 | Nipper | 40 |  |  | Not Started
1.11.3 | Contracts & Invoice data review — C1/C2, vendors, invoices, check runs | 2026-08-10 | 2026-09-18 | Salzwedel | 24 |  |  | Not Started
1.11.3 | Contracts & Invoice data review — C1/C2, vendors, invoices, check runs | 2026-08-10 | 2026-09-18 | Chang | 44 |  |  | Not Started
1.11.3 | Contracts & Invoice data review — C1/C2, vendors, invoices, check runs | 2026-08-10 | 2026-09-18 | Lee | 44 |  |  | Not Started
1.11.4 | Funding & AccuFund sync data review — grants, allotments, DIAs, GL sync | 2026-09-14 | 2026-10-09 | Nipper | 20 |  |  | Not Started
1.11.4 | Funding & AccuFund sync data review — grants, allotments, DIAs, GL sync | 2026-09-14 | 2026-10-09 | Nassayan | 20 |  | AccuFund sync table expertise | Not Started
1.11.5 | Final data validation & cleanup signoff (gates Migration Dry Run 2) | 2026-10-05 | 2026-10-16 | Cole | 24 |  |  | Not Started
1.11.5 | Final data validation & cleanup signoff (gates Migration Dry Run 2) | 2026-10-05 | 2026-10-16 | Nipper | 8 |  |  | Not Started
1.11.5 | Final data validation & cleanup signoff (gates Migration Dry Run 2) | 2026-10-05 | 2026-10-16 | Salzwedel | 20 |  | ACTC compliance signoff | Not Started
M3.5 | ★ Data Cleanup Complete — gates Migration Dry Run 2 and Dashboard Finalization |  | 2026-10-16
1.7 | Data Migration | 2026-08-01 | 2026-10-23
1.7.1 | Migration scripts (SQL Server → Supabase) | 2026-08-01 | 2026-09-15 | Nassayan | 80 |  | Selective — bad data excluded | Not Started
1.7.1 | Migration scripts (SQL Server → Supabase) | 2026-08-01 | 2026-09-15 | Cole | 16 |  |  | Not Started
1.7.2 | Dry Run 1 & 2 — migrate, validate, iterate | 2026-09-15 | 2026-10-23 | Nassayan | 48 |  |  | Not Started
1.7.2 | Dry Run 1 & 2 — migrate, validate, iterate | 2026-09-15 | 2026-10-23 | Cole | 12 |  |  | Not Started
1.7.3 | Migration documentation & data dictionary | 2026-10-06 | 2026-10-23 | Nipper | 16 |  |  | Not Started
1.7.4 | Migration testing | 2026-10-06 | 2026-10-23 | Chang | 24 |  |  | Not Started
1.7.4 | Migration testing | 2026-10-06 | 2026-10-23 | Lee | 24 |  |  | Not Started
M4 | ★ Migration Validated (Dry Run 2 passes) |  | 2026-10-23
1.8 | Cross-cutting Features | 2026-09-01 | 2026-10-30
1.8.1 | AI Assistant — chat panel, knowledge base, context tools | 2026-09-01 | 2026-10-16 | Mortazavi | 48 |  | Architecture + prompts | Not Started
1.8.1 | AI Assistant — chat panel, knowledge base, context tools | 2026-09-01 | 2026-10-16 | Cole | 28 |  |  | Not Started
1.8.1 | AI Assistant — chat panel, knowledge base, context tools | 2026-09-01 | 2026-10-16 | Brown | 32 |  |  | Not Started
1.8.2 | Tooltips, PMI terminology, training module, org chart | 2026-09-15 | 2026-10-16 | Nipper | 28 |  | PMI standards + 30 definitions | Not Started
1.8.2 | Tooltips, PMI terminology, training module, org chart | 2026-09-15 | 2026-10-16 | Cole | 16 |  |  | Not Started
1.8.2 | Tooltips, PMI terminology, training module, org chart | 2026-09-15 | 2026-10-16 | Brown | 16 |  |  | Not Started
1.8.3 | Print/export on all modules (PDF + Excel, ACTC branded) | 2026-10-10 | 2026-10-23 | Cole | 8 |  |  | Not Started
1.8.3 | Print/export on all modules (PDF + Excel, ACTC branded) | 2026-10-10 | 2026-10-23 | Brown | 12 |  |  | Not Started
1.9 | Tableau Reporting Setup — Phase 1 (Build → Finalize dependency chain) | 2026-08-01 | 2026-11-06
1.9.1 | 1.9a Build — BigQuery reporting views & materialized tables (once schema live) | 2026-08-01 | 2026-09-15 | Nassayan | 100 |  | Analytics layer; starts after M1 | Not Started
1.9.2 | 1.9a Build — Tableau Cloud connection & core internal dashboards (development) | 2026-09-01 | 2026-10-10 | Nassayan | 120 |  | Budget/contract/invoice/funding; refined as data cleans up | Not Started
1.9.3 | 1.9b Finalize — Dashboard validation & finalization against cleaned data (post-M3.5) | 2026-10-19 | 2026-10-30 | Nassayan | 40 |  | Gated by M3.5 Data Cleanup Complete | Not Started
1.9.4 | 1.9b Finalize — Susan's Reporting Template dashboard | 2026-10-26 | 2026-11-06 | Nassayan | 40 |  | Per ACTC reporting template | Not Started
1.9.4 | 1.9b Finalize — Susan's Reporting Template dashboard | 2026-10-26 | 2026-11-06 | Cole | 8 |  | Requirements + review | Not Started
1.9.5 | Tableau reporting documentation (both build and finalize phases) | 2026-10-15 | 2026-11-06 | Nipper | 12 |  |  | Not Started
1.10 | UAT & Go-Live Prep | 2026-10-12 | 2026-10-30
1.10.1 | User acceptance testing | 2026-10-12 | 2026-10-23 | Chang | 36 |  |  | Not Started
1.10.1 | User acceptance testing | 2026-10-12 | 2026-10-23 | Lee | 36 |  |  | Not Started
1.10.2 | Bug fixes, stabilization, AI Intake tuning | 2026-10-19 | 2026-10-30 | Cole | 20 |  |  | Not Started
1.10.2 | Bug fixes, stabilization, AI Intake tuning | 2026-10-19 | 2026-10-30 | Brown | 16 |  |  | Not Started
1.10.2 | Bug fixes, stabilization, AI Intake tuning | 2026-10-19 | 2026-10-30 | Mortazavi | 24 |  | AI accuracy validation | Not Started
1.10.3 | Go-live readiness & compliance signoff | 2026-10-26 | 2026-10-30 | Salzwedel | 12 |  |  | Not Started
1.10.4 | Admin & user guide finalization | 2026-10-20 | 2026-10-30 | Nipper | 24 |  |  | Not Started
Phase 1 Subtotal
M5 | ★ Phase 1 MVP Go-Live (parallel operation begins) |  | 2026-10-30
1.5A | PHASE 1.5: AI DATA ACCESS (Nov 2026) | 2026-11-02 | 2026-11-30
1.5A.1 | query_pcs_data tool — top 20 query templates | 2026-11-02 | 2026-11-20 | Mortazavi | 40 |  |  | Not Started
1.5A.1 | query_pcs_data tool — top 20 query templates | 2026-11-02 | 2026-11-20 | Cole | 20 |  |  | Not Started
1.5A.1 | query_pcs_data tool — top 20 query templates | 2026-11-02 | 2026-11-20 | Brown | 20 |  |  | Not Started
1.5A.2 | Knowledge base admin, AI Invoice Intake rule expansion | 2026-11-10 | 2026-11-30 | Mortazavi | 28 |  | Refine from MVP feedback | Not Started
1.5A.2 | Knowledge base admin, AI Invoice Intake rule expansion | 2026-11-10 | 2026-11-30 | Cole | 12 |  |  | Not Started
1.5A.2 | Knowledge base admin, AI Invoice Intake rule expansion | 2026-11-10 | 2026-11-30 | Brown | 12 |  |  | Not Started
1.5A.3 | Phase 1.5 documentation & testing | 2026-11-20 | 2026-11-30 | Nipper | 8 |  |  | Not Started
1.5A.3 | Phase 1.5 documentation & testing | 2026-11-20 | 2026-11-30 | Chang | 12 |  |  | Not Started
1.5A.3 | Phase 1.5 documentation & testing | 2026-11-20 | 2026-11-30 | Lee | 12 |  |  | Not Started
Phase 1.5 Subtotal
M6 | ★ AI Data Access Live |  | 2026-11-30
2 | PHASE 2: EXTENDED MODULES (Dec 2026 – Feb 2027) | 2026-12-01 | 2027-02-19
2.1 | Requisitions / procurement workflow (12-stage) | 2026-12-01 | 2027-01-09 | Cole | 32 |  |  | Not Started
2.1 | Requisitions / procurement workflow (12-stage) | 2026-12-01 | 2027-01-09 | Brown | 28 |  |  | Not Started
2.2 | Contract Equity, Insurance, Staffing modules | 2026-12-15 | 2027-01-23 | Cole | 28 |  |  | Not Started
2.2 | Contract Equity, Insurance, Staffing modules | 2026-12-15 | 2027-01-23 | Brown | 20 |  |  | Not Started
2.2 | Contract Equity, Insurance, Staffing modules | 2026-12-15 | 2027-01-23 | Nassayan | 20 |  | DB tables | Not Started
2.3 | PM Update module + .mpp import/export | 2027-01-05 | 2027-01-30 | Cole | 24 |  |  | Not Started
2.3 | PM Update module + .mpp import/export | 2027-01-05 | 2027-01-30 | Brown | 24 |  |  | Not Started
2.4 | Cloud document storage & file server sync | 2027-01-12 | 2027-02-06 | Cole | 12 |  |  | Not Started
2.4 | Cloud document storage & file server sync | 2027-01-12 | 2027-02-06 | Brown | 20 |  |  | Not Started
2.5 | AccuFund integration connector | 2027-01-19 | 2027-02-13 | Nassayan | 32 |  |  | Not Started
2.5 | AccuFund integration connector | 2027-01-19 | 2027-02-13 | Cole | 8 |  |  | Not Started
2.6 | Advanced reporting, Slack/Teams integration | 2027-01-26 | 2027-02-13 | Brown | 20 |  |  | Not Started
2.6 | Advanced reporting, Slack/Teams integration | 2027-01-26 | 2027-02-13 | Cole | 8 |  |  | Not Started
2.7 | AI voice I/O + expanded query templates (30-50) | 2027-01-19 | 2027-02-13 | Mortazavi | 40 |  |  | Not Started
2.7 | AI voice I/O + expanded query templates (30-50) | 2027-01-19 | 2027-02-13 | Cole | 8 |  |  | Not Started
2.7 | AI voice I/O + expanded query templates (30-50) | 2027-01-19 | 2027-02-13 | Brown | 12 |  |  | Not Started
2.8 | Tableau — Public-Facing Visualizations | 2026-12-01 | 2027-02-19
2.8.1 | Public project funding status dashboards | 2026-12-01 | 2027-01-09 | Nassayan | 72 |  | Commission/public access | Not Started
2.8.2 | Program expenditure & investment map visualizations | 2027-01-05 | 2027-01-30 | Nassayan | 68 |  | Geographic/program views | Not Started
2.8.3 | Tableau embed config, public access & security | 2027-01-26 | 2027-02-13 | Nassayan | 48 |  |  | Not Started
2.9 | Phase 2 documentation | 2027-02-03 | 2027-02-19 | Nipper | 20 |  |  | Not Started
2.10
2.10 | Phase 2 testing | 2027-02-03 | 2027-02-19 | Lee | 32 |  |  | Not Started
2.11 | Phase 2 compliance review | 2027-02-10 | 2027-02-19 | Salzwedel | 16 |  |  | Not Started
Phase 2 Subtotal
M7 | ★ Phase 2 Complete (extended modules + public Tableau) |  | 2027-02-19
3 | PHASE 3: OPTIMIZATION (Mar – Apr 2027) | 2027-03-01 | 2027-04-30
3.1 | Full AccuFund bidirectional sync | 2027-03-01 | 2027-03-20 | Nassayan | 40 |  |  | Not Started
3.1 | Full AccuFund bidirectional sync | 2027-03-01 | 2027-03-20 | Cole | 12 |  |  | Not Started
3.2 | Advanced workflows, bulk ops, external API | 2027-03-08 | 2027-04-03 | Cole | 28 |  |  | Not Started
3.2 | Advanced workflows, bulk ops, external API | 2027-03-08 | 2027-04-03 | Brown | 32 |  |  | Not Started
3.3 | Performance optimization & load testing | 2027-04-01 | 2027-04-18 | Cole | 12 |  |  | Not Started
3.3 | Performance optimization & load testing | 2027-04-01 | 2027-04-18 | Brown | 12 |  |  | Not Started
3.3 | Performance optimization & load testing | 2027-04-01 | 2027-04-18 | Nassayan | 24 |  | DB tuning | Not Started
3.4 | Tableau polish & public dashboard launch | 2027-03-15 | 2027-04-18 | Nassayan | 48 |  | Final refinement | Not Started
3.5 | Production cutover prep (legacy retirement) | 2027-04-14 | 2027-04-30 | Cole | 20 |  |  | Not Started
3.5 | Production cutover prep (legacy retirement) | 2027-04-14 | 2027-04-30 | Nassayan | 16 |  |  | Not Started
3.6 | AI Invoice Intake — production optimization | 2027-04-07 | 2027-04-25 | Mortazavi | 20 |  | Accuracy metrics review | Not Started
3.7 | Phase 3 documentation | 2027-04-07 | 2027-04-25 | Nipper | 20 |  | Final guide updates | Not Started
3.8 | Phase 3 testing | 2027-04-07 | 2027-04-25 | Chang | 20 |  |  | Not Started
3.8 | Phase 3 testing | 2027-04-07 | 2027-04-25 | Lee | 20 |  |  | Not Started
3.9 | Final compliance review & signoff | 2027-04-14 | 2027-04-25 | Salzwedel | 16 |  |  | Not Started
Phase 3 Subtotal
M8 | ★ Production Cutover (legacy retired) |  | 2027-04-30
PM | PROJECT MANAGEMENT (ongoing) | 2026-05-01 | 2027-04-30
PM.1 | Project oversight & stakeholder coordination | 2026-05-01 | 2027-04-30 | Cole | 68 |  | ~5 hrs./month × 12 | Not Started
PM.2 | Technical architecture reviews | 2026-05-01 | 2027-04-30 | Mortazavi | 56 |  | ~3 hrs./month × 12 | Not Started
PM.3 | ACTC coordination meetings | 2026-05-01 | 2027-04-30 | Salzwedel | 16 |  | ~1.3 hrs./month × 12 | Not Started
PM.4 | Risk management & change control | 2026-05-01 | 2027-04-30 | Nipper | 20 |  | ~1.7 hrs./month × 12 | Not Started
Project Management Subtotal
GRAND TOTAL
RESOURCE SUMMARY
Resource | Firm | B7 Classification | B7 Rate (2026) | Hours | Cost | Role on PCS
Chris Cole | CME (Prime) | Project Manager/President/CEO | 407.04 |  |  | Project Lead — leads every module
Ali Mortazavi | DAVTEQ | Principal & Project Manager | 278.3 |  |  | AI Architect
Jason Brown | DAVTEQ | Sr. Full Stack Software & AI Engineer | 217.8 |  |  | Developer (supporting role)
Tom Nassayan | SQL & Sightline Solutions | President/CEO | 260 |  |  | Database & Tableau
Mark Nipper | CME (Prime) | PC Specialist | 341.01 |  |  | Documentation Lead (ALL docs)
Steven Salzwedel | ACUMEN | PC Advisor | 216.66 |  |  | ACTC Compliance & Standards
Eric Chang | Tricertus LLC | Programming PC/Support | 102.89 |  |  | Testing (replaces Pearl Chu)
Hanuel Lee | Tricertus LLC | PC Administrator | 114.65 |  |  | Testing (replaces Kristy Ou)
TOTAL
MILESTONE SUMMARY
# | Milestone |  |  | Target Date
M1 | Infrastructure Complete (Auth, RLS, Workflow Engine) |  |  | 2026-06-27
M2 | Core Modules Complete (Programming, Projects, Contracts) |  |  | 2026-09-18
M3 | All Core Modules Complete (Invoice + Funding workflows) |  |  | 2026-10-16
M3.5 | Data Cleanup Complete — gates Migration & Dashboard Finalization |  |  | 2026-10-16
M4 | Migration Validated (Dry Run 2 passes) |  |  | 2026-10-23
M5 | Phase 1 MVP Go-Live (parallel operation begins) |  |  | 2026-10-30
M6 | AI Data Access Live |  |  | 2026-11-30
M7 | Phase 2 Complete (extended modules + public Tableau) |  |  | 2027-02-19
M8 | Production Cutover (legacy retired) |  |  | 2027-04-30
VERSION HISTORY
v8 (Apr 19, 2026): Added Status column (I). All 181 task rows set to Not Started — the contract has not yet begun (kickoff May 1, 2026). Statuses: Not Started, In Development, Submitted for Review, Accepted, Rejected, Deferred. Only CME Admin can set Accepted, triggered by recording an ACTC acceptance.
v8 (Apr 19, 2026): Clarified that the Claude Code prototype at actc-pcs.vercel.app is pre-contract CME investment for de-risking — not a workplan deliverable. Does not consume contracted hours. When contract begins May 1, the prototype is a starting reference only; all 4,912 hours remain to be performed.
v8 (Apr 19, 2026): Rate escalation policy — 2026 rates apply to 2026 work; 2027 work escalates 3% per calendar year (Jan 1). Baseline cost $1,356,256 at 2026 rates; actual invoiced costs use escalation via CME Client Portal date-effective rate engine.
v7 (Apr 16, 2026): Added Section 1.0 Database Learning & Restructuring (160 hrs: Cole 64, Nassayan 96) — delivers data dictionary that feeds schema design (1.1.1) and cleanup plan (1.11). Starts at kickoff (May 1, 2026).
v7 (Apr 16, 2026): Added Section 1.11 PCS Data Review & Cleanup (400 hrs: Nipper 120, Salzwedel 60, Chang 80, Lee 80, Cole 40, Nassayan 20). Parallel to module builds, Jun 15 – Oct 16, 2026. New M3.5 milestone gates Migration Dry Run 2 and Dashboard Finalization.
v7 (Apr 16, 2026): Restructured Tableau 1.9 into Build→Finalize dependency chain. 1.9a Build = BigQuery views + core dashboards (existing hrs). 1.9b Finalize = post-M3.5 validation (Nassayan 40 new) + Susan's Reporting Template dashboard (Nassayan 40 + Cole 8 new). Docs relabeled 1.9.5.
v7 (Apr 16, 2026): Updated milestone list to 9 gates (M1, M2, M3, M3.5, M4, M5, M6, M7, M8). Extended Phase 1 end date from Oct 30 to Nov 6, 2026 to cover dashboard finalization. Added +604 hrs / +$160,488 total to project (v6: 4,308 hrs / $1,195,768 → v7: 4,912 hrs / $1,356,256).
v7 (Apr 16, 2026): Cleanup of v6 artifacts — filled missing dates on module testing rows (1.2.5, 1.3.4, 1.4.7, 1.6.4); deleted empty merged PM.3 row and renumbered PM.4→PM.3, PM.5→PM.4.
v6 (Apr 16, 2026): Integrated rA1 contract deliverables — 45 tasks cross-referenced to workplan WBS
v6 (Apr 16, 2026): Added module testing for Programming, Projects, Contracts, Funding (per Mark #3, #13, #21)
v6 (Apr 16, 2026): Added Management Disciplines sheet (#14-18) and Acronyms & Definitions (#4, #11)
v6 (Apr 16, 2026): Fixed resource names: Eric Chang, Hanuel Lee (per Mark v5); fixed SUMPRODUCT formulas
v4 (Apr 14, 2026): Doubled Ali (222→444), Jason (472→944), Tom (528→1,056); halved Steven (192→96)
v4 (Apr 14, 2026): Added AI Invoice Intake — document ingestion, field extraction, compliance analysis, review dashboard
v4 (Apr 14, 2026): Added Tableau public-facing visualizations (Tom, spanning Phase 1–2)
v4 (Apr 14, 2026): Tom role expanded: Database & Tableau reporting (internal + public-facing)
v3 (Apr 14, 2026): Initial workplan with corrected roles, rates from B7, team structure
STATUS LEGEND
Not Started | Planned per workplan; work has not yet begun under the contract (status of all rows as of April 19, 2026).
In Development | Work is actively underway under the contract after May 1, 2026. Not yet submitted to ACTC.
Submitted for Review | Formally submitted to ACTC for review; awaiting feedback or acceptance.
Accepted | ACTC has formally accepted. Only CME Admin can set this status.
Rejected | ACTC reviewed and explicitly rejected. Requires CME response.
Deferred | Descoped or postponed beyond the current plan.

## Contract Deliverables (rA1)
Contract Deliverables Cross-Reference — Work Plan rA1
Maps R26-003 contract scope items to PCS SaaS Development Workplan WBS items
Seq | Task | Contract Deliverable | Owner | Freq | Delivery | Workplan WBS Reference | Status
TASK 1: PROJECT CONTROLS SUPPORT
1 | 1 | Develop Work Plan | CC/MN | Annually | Apr 2026 | This workplan (v6) | In Progress
2 | 1 | Develop System for documenting Correspondence | CC/MN/SS | Once | Apr 2027 | 1.4 (Contracts docs), 2.4 (Cloud Storage) | Phase 1-2
3 | 1 | Draft Project Controls Forms | MN/SS | Once | Aug 2026 | 1.8.2 (PMI terminology/tooltips), Nipper docs | Phase 1
4 | 1 | Compile Funding and PC Data | MN/SS | Monthly | Ongoing | 1.6 (Funding), 1.9 (Tableau), PM.5 | Phase 1+
5 | 1 | Develop system to maintain PC Data | CC/MN/SS | Once | Apr 2027 | 1.1-1.10 (entire PCS SaaS build = this system) | Phase 1
6 | 1 | Prepare Analytical Reports | MN/SS | Monthly | Ongoing | 1.9 (Tableau), 2.8 (Public Viz), 2.6 (Adv Reporting) | Phase 1+
7 | 1 | Draft Project Controls Monitoring Reports | MN/SS | Once | Aug 2026 | 1.3.2 (Cost/Schedule Reports per rA2) | Phase 1
8 | 1 | Support Mid-year & Annual FY Budgets | CC/MN/SS | Annually | Ongoing | 1.4.4 (Time-phased budgets, WF-23/24) | Phase 1+
9 | 1 | Assist in drafting Agenda Packages | MN/SS | As req | Ongoing | 1.8.3 (Print/export, ACTC branded PDF) | Phase 1+
TASK 2: PROJECT DELIVERY SUPPORT
10 | 2 | Draft Change Management Procedures | MN | Once | Aug 2026 | 1.4.2 (C1/C2), WF-11/12/13, Nipper docs | Phase 1
11 | 2 | Draft Risk Management Procedures | MN | Once | Aug 2026 | PM.5 (Risk mgmt), Nipper documentation | Phase 1
12 | 2 | Draft Schedule Development/Mgmt Procedures | MN | Once | Aug 2026 | 1.3.2 (Schedule Reports), 2.3 (.mpp import/export) | Phase 1
13 | 2 | Maintain Project Delivery Data (financials, deadlines, costs) | MN/SS/HL/EC | Monthly | Ongoing | 1.3 (Projects), 1.5 (Invoices), PCS operations | Phase 1+
14 | 2 | Refine PC Processes, Tools, Reports & Delivery Plans | CC/MN/SS | Once | Aug 2026 | 1.1.3 (Workflow engine), 1.8.2 (PMI), 3.2 (Adv WF) | Phase 1-3
15 | 2 | Develop PC Procedures for project/program monitoring | MN/SS | Once | Aug 2026 | 1.8.2 (PMI standards), Nipper Phase 1 docs | Phase 1
16 | 2 | Prepare/review Delivery Plans, Cost/Schedule Controls | MN/SS/HL/EC | Once | Aug 2026 | 1.3.2 (Cost/Schedule Reports rA2), 1.9 (Tableau) | Phase 1
17 | 2 | Work with Delivery Team to maintain PM information | MN/SS | Monthly | Ongoing | 1.3 (Projects Module), PM.1 | Phase 1+
18 | 2 | Develop Change Management Plan (contract compliance) | MN/SS | Once | Aug 2026 | 1.4.3 (Contract workflows WF-09/10), Nipper docs | Phase 1
19 | 2 | Assist with Cost and Schedule Controls management | MN/SS | Monthly | Ongoing | 1.3.2, 1.4.4 (WF-23), PM.4 | Phase 1+
20 | 2 | PC Admin: maintain data, reconcile costs, funding plans | HL/EC | Monthly | Ongoing | 1.5 (Invoices), 1.6 (Funding), PCS operations | Phase 1+
21 | 2 | Record funding agreement information in PCS | HL/EC | Monthly | Ongoing | 1.6 (Funding — grants, allotments, DIAs) | Phase 1+
22 | 2 | Prepare financial and funding reports | MN/SS | As req | Ongoing | 1.9 (Tableau), 2.8 (Public Viz), 2.6 (Reporting) | Phase 1+
23 | 2 | Implement Change Mgmt & Document Control for PCS | CC | Once | Apr 2027 | 1.1.3 (Workflow engine), 1.4 (Contracts), 2.4 (Cloud) | Phase 1-2
24 | 2 | Analyze system design, develop PCS, support DB programming | CC | Once | Apr 2027 | 1.1 (Infrastructure), entire Phase 1 build | Phase 1
25 | 2 | Review system, implement tools to improve PC data | CC | Once | Aug 2026 | 1.5.1-1.5.4 (AI Invoice Intake), 1.8.1 (AI Assistant) | Phase 1
26 | 2 | Modify, delete, develop database modules as required | CC | Once | Apr 2027 | 1.2-1.6 (module builds), 2.1-2.8 (Phase 2) | Phase 1-2
27 | 2 | Support infrastructure / technical DB programming | CC | As req | Ongoing | 3.2 (Adv workflows), 3.3 (Perf), 3.5 (Cutover) | Phase 1-3
28 | 2 | Design/develop Project, Contract, Invoice Dashboards | CC | Once | Apr 2027 | 1.1.5 (Home dashboard), 1.9/2.8 (Tableau) | Phase 1-2
29 | 2 | Perform QA/QC of prepared Reports | CC/MN/SS | Monthly | Ongoing | 1.10 (UAT), PM.1/PM.5, all testing tasks | Ongoing
30 | 2 | Optimize the System | CC | As req | Ongoing | 3.1-3.5 (Phase 3 Optimization) | Phase 3
31 | 2 | Develop/enhance PC Processes for Budgets, Estimates, Schedules | CC/MN/SS | Once | Aug 2026 | 1.3.2, 1.4.4 (WF-23/24), 1.8.2 (PMI) | Phase 1
32 | 2 | General Cost/Schedule/Systems/Risk Mgmt support | MN/SS | Monthly | Ongoing | PM.4/PM.5, all Salzwedel reviews | Ongoing
33 | 2 | Deliverables: PCS, Monitoring Rpts, Funding Plans, Expiration Rpts, PMO, Strategic Plan | CC/MN/SS | As req | Ongoing | 1.2-1.6 (modules), 1.9/2.8 (Tableau), all docs | Phase 1+
TASK 3: PROGRAMMING & FUND MANAGEMENT SUPPORT
34 | 3 | Guidance on Strategic Programming Approaches | CC | As req | Ongoing | 1.2 (Programming), PM.1 | Phase 1+
35 | 3 | Develop policies/procedures for Programming & Oversight | CC/MN/SS | Once | Phase 1 | 1.2.2 (CIP workflow), Nipper docs | Phase 1
36 | 3 | PM Oversight of externally implemented projects | CC/MN/SS | As req | Ongoing | 1.3 (Projects), 1.9/2.8 (Tableau) | Phase 1+
37 | 3 | Develop processes for Fund Program Admin & Oversight | MN/SS | Once | Phase 1 | 1.6 (Funding Module), Nipper docs | Phase 1
38 | 3 | Improve grant administration | CC/MN/SS | As req | Ongoing | 1.6 (Funding — grants, closeouts) | Phase 1+
39 | 3 | Federal/state funding support (Caltrans, DBE) | CC/MN/SS | As req | Ongoing | 2.2 (Contract Equity — LBE/SLBE/DBE) | Phase 2
40 | 3 | Support CIP preparation for Commission approval | CC/MN/SS | As req | Ongoing | 1.2 (Programming — CIP amendments), 2.8 (Public Viz) | Phase 1+
41 | 3 | Prepare funding agreements using templates | MN/SS | As req | Ongoing | 1.6 (Funding Module — DIA/grant templates) | Phase 1+
42 | 3 | Support PMs with funding and procedural matters | CC/MN/SS | As req | Ongoing | 1.8.1 (AI Assistant), 1.3 (Projects), PM.1 | Phase 1+
43 | 3 | Develop PMO & grant monitoring reports | CC/MN/SS | Once | Aug 2026 | 1.9 (Tableau), 2.8 (Public Viz), 2.6 (Reporting) | Phase 1-2
44 | 3 | Deliverables: Strategic Plan, cashflow, CIP, agreements, PMO/Grant Rpts, dashboards | CC/MN/SS | As req | Ongoing | 1.2/1.6 (Prog/Fund), 1.9/2.8 (Tableau), all docs | Phase 1+
OPTIONAL TASK O1
45 | O1 | Create / rollout PCS #2 | CC/MN/SS | Once | Apr 2027 | THIS IS THE PCS SaaS PROJECT — WBS 1.1 through M8 | In Progress

## Management Disciplines
Management Discipline → PCS Module Mapping
Addresses Mark's questions #14-18: Where does each discipline live in the new system?
Discipline | Where It Lives in PCS SaaS | Workplan WBS
Cost Management (#14) | Contracts Module (task/vendor budgets, C1/C2 reallocations), Invoice Module (approval routing, IPV/CSR, short pay, retention), Project Cost Report (per rA2), Time-phased budgets (WF-24), Budget Change Request (WF-23) | 1.4, 1.5, 1.3.2
Risk Management (#15) | Workflow engine tracks approval compliance, AI Invoice Intake flags rate/budget/cost code exceptions, Contract expiration monitoring, Grant closeout tracking, Exception reports | 1.1.3, 1.5.1-1.5.4, PM.5
Schedule Management (#16) | Projects Module — Schedule Report (per rA2), .mpp import/export for full WBS hierarchy, baseline vs current comparison in PM Update view | 1.3.2, 2.3
Change Management (#17) | Workflow engine (WF-09-13): contract amendments, C1/C2 reallocations, task order auth. Full audit trail. Budget Change Request (WF-23) with configurable thresholds. | 1.4.2-1.4.4, 1.1.3
Document Control (#18) | Contract documents tab, Cloud storage with file server sync (Phase 2), Print/export (PDF + Excel, ACTC branded), Correspondence system, AI knowledge base | 1.4, 2.4, 1.8.3, 1.8.1
Forecasting (#12) | Both levels: Project (ETC, EAC, committed amounts in PM Update) and Contract (time-phased monthly budgets, distribution tool, versioning). Tableau dashboards for trends. | 1.3.2, 1.4.4, 1.9
User Acceptance (#21) | WBS 1.10 — dedicated UAT with Chang + Lee, plus per-module testing on all core modules. Salzwedel compliance signoff at go-live. | 1.10, module testing rows
PC Process Alignment (#20) | All 24 workflows modeled from current ACTC procedures. PMI terminology on all fields. Visual workflow editor lets admins adjust without code. Nipper validates. | 1.1.3, 1.8.2, Nipper tasks

## Acronyms & Definitions
Acronyms & Definitions
Term | Definition
ACTC | Alameda County Transportation Commission
AI | Artificial Intelligence — used for Invoice Intake OCR and built-in Chat Assistant
BigQuery / BQ | Google BigQuery — analytics database feeding Tableau Cloud reporting
C1 Form | Contract task budget reallocation form
C2 Form | Contract vendor budget reallocation form
CIP | Comprehensive Investment Plan
CSR | Contract Status Report — auto-generated with invoice packages
DBE | Disadvantaged Business Enterprise
DIA | Direct Implementation Agreement — a funding agreement type
EAC | Estimate at Completion (PMI) — total expected cost at project finish
ETC | Estimate to Complete (PMI) — remaining cost to finish
FY | Fiscal Year
IPV | Invoice Payment Voucher — auto-generated for approval routing
ISL | Invoice Status Log — Excel today, replaced by in-app module
LBE | Local Business Enterprise
MVP | Minimum Viable Product — Phase 1 go-live target
OAuth | Open Authorization — secure login via Google/Microsoft accounts
PCA | Project Controls Assistant — primary data entry role
PCS | Project Controls System — the legacy system being replaced
PFA | Pass-through Funding Agreement — a contract type
PM | Project Manager
PMI | Project Management Institute — source for standard terminology
PMO | Project Management Oversight
PNRF | Project Number Request Form — workflow for new project creation
PO | Purchase Order
PSA | Professional Services Agreement — a contract type
RLS | Row-Level Security — database access control per user
SaaS | Software as a Service — cloud-hosted web application
SLBE | Small Local Business Enterprise
Supabase | Cloud PostgreSQL platform — primary application database
Tableau | Tableau Cloud — business intelligence / visualization platform
UAT | User Acceptance Testing
WBS | Work Breakdown Structure
WF-## | Workflow number (e.g., WF-03 = Invoice Approval Routing) — 24 tracked workflows

## Mark Comments (v5)
Sequence # | Thoughts
1 | Formatted a bit
Cleaned up team member names a bit
Programming, Projects, Contracts Module Testing not present
A definition associated with each section and associated capabilities would be very helpful
The Work Plan comes across like a resource loaded, software building schedule
The Work Plan I envisioned was a task by task listing of our contract based work deliverables with associated details
How are work tasks derived?
How are durations derived?
How are hours derived?
How is schedule logic derived?
Acronyms may require definition
Are we "forecasting" at the Project or Contracts level?
Funding Module Testing not present
Where do we establish / create Cost Management functionality?
Where do we establish / create Risk Management functionality?
Where do we establish / create Schedule Management functionality?
Where do we establish / create Change Management functionality?
Where do we establish / create Document Control / Management functionality?
Do we want required functionality needs / goals from our User Community?
Will the "Tool Design" coincide with our PC processes and procedures? Very important!
Will we have an "Overall User Testing / Acceptance" phase?